## Calendar
Week # | September
| Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday
|  |  |  | 1 | 2 | 3 | 4
| 5 | 6 | 7 | 8 | 9 | 10 | 11
| 12 | 13 | 14 | 15 | 16 | 17 | 18
| 19 | 20 | 21 | 22 | 23 | 24 | 25
1 | 26 | 27 | 28 | 29 | 30
October
| Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday
1 | [5 empty] | 1 | 2
2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
3 | 10 | 11 | 12 | 13 | 14 | 15 | 16
4 | 17 | 18 | 19 | 20 | 21 | 22 | 23
5 | 24 | 25 | 26 | 27 | 28 | 29 | 30
6 | 31
November
| Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday
6 |  | 1 | 2 | 3 | 4 | 5 | 6
7 | 7 | 8 | 9 | 10 | 11 | 12 | 13
8 | 14 | 15 | 16 | 17 | 18 | 19 | 20
9 | 21 | 22 | 23 | 24 | 25 | 26 | 27
10 | 28 | 29 | 30
December
| Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday
10 |  |  |  | 1 | 2 | 3 | 4
11 | 5 | 6 | 7 | 8 | 9 | 10 | 11
12 | 12 | 13 | 14 | 15 | 16 | 17 | 18
13 | 19 | 20 | 21 | 22 | 23 | 24 | 25
14 | 26 | 27 | 28 | 29 | 30 | 31

## MGMT_Calendar
Calendar for OGP Process
Select a period to highlight at right. A legend describing the charting follows. | [10 empty] | Period Highlight: | 19 | [7 empty] | Plan Duration |  |  | Actual Start |  |  | % Complete |  |  | Actual (beyond plan) |  |  |  | % Complete (beyond plan)
ACTIVITY | RESPONSIBILITY | STATUS | NOTES | WEEK # | PROPOSED DEADLINE | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | DATE COMPLETED | % COMPLETE
[12 empty] | SEPTEMBER | [7 empty] | OCTOBER | [30 empty] | NOVEMBER | [29 empty] | DECEMBER
[12 empty] | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
General Tasks
Templates
Specific stakeholder feedback tools 1 | POC / Technical Secretariat | Completed |  | 1 | 2020-09-25 | 23 | 3 | 23 | 3 | 2020-09-25 | 100%
Specific stakeholder feedback tools 2 | POC / Technical Secretariat | Completed |  | 1 | 2020-09-25 | 23 | 3 | 23 | 3 | 2020-09-25 | 100%
General Stakeholder Feedback Tool | POC / Technical Secretariat | Completed |  | 2 | 2020-10-08 | 2 | 6 | 2 | 6 | 2020-10-08 | 100%
Consultation Report Template | POC / Technical Secretariat | Completed |  | 2 | 2020-10-05 | 1 | 5 | 3 | 3 | 2020-10-05 | 100%
Consultation Report Feedback Template | POC / Technical Secretariat | Completed |  | 2 | 2020-10-08 | 5 | 4 | 5 | 4 | 2020-10-08 | 100%
Drafts
Explanatory Note for Entire Process | POC / Technical Secretariat | Pending |  | 4 | 2020-10-22 | 20 | 2
Explanatory Note for Methodology | POC / Technical Secretariat | Pending |  | 4 | 2020-10-22 | 20 | 2
Explanatory Note for Co-Creation Process | POC / Technical Secretariat | Pending |  | 4 | 2020-10-22 | 20 | 2
State of Play | POC / Technical Secretariat | Pending |  | 4 | 2020-10-22 | 21 | 1
Consultation with Council of CSOs and Citizens
Summary Note of Consultation Process | POC / Technical Secretariat | Pending |  | 4 | 2020-10-23 | 21 | 2
Agenda for 9th November Meeting | POC / Technical Secretariat | Pending |  | 4 | 2020-10-23 | 21 | 2
Consultation Tools Developed | POC / Technical Secretariat | Pending |  | 4 | 2020-10-23 | 21 | 2
CSP Council Consultation | POC / Technical Secretariat | Pending | tentative date proposed | 7 | 2020-11-09
Consultation in the E-Register | POC / Technical Secretariat | Pending | tentative date proposed | 5 | 2020-10-30
Access to Justice
Stakeholder Resources and Tools
Component Brief | POC / Technical Secretariat | Completed |  | 1 | 2020-09-28 | 25 | 3 | 25 | 3 | 2020-09-28 | 100%
Feedback Template 1 Designed | POC / Technical Secretariat | Completed |  | 1 | 2020-09-28 | 23 | 5 | 23 | 5 | 2020-09-28 | 100%
Feedback Template 2 Designed | POC / Technical Secretariat | Completed |  | 1 | 2020-09-28 | 23 | 5 | 23 | 5 | 2020-09-28 | 100%
Feedback Template 1 Converted to GoogleForms | POC / Technical Secretariat | Completed |  | 1 | 2020-10-02 | 1 | 1 | 1 | 1 | 2020-10-02 | 100%
Feedback Template 2 Converted to GoogleForms | POC / Technical Secretariat | Completed |  | 2 | 2020-10-08 | 6 | 2 | 6 | 1 | 2020-10-07 | 100%
Link to Online Feedback | MoJ | Completed |  | 2 | 2020-10-08 | 8 | 1 | 7 | 1 | 2020-10-07 | 100%
1 Consultation
Pre-consultation discussion and strategy meeting with POC | POC / Technical Secretariat | Completed |  | 1 | 2020-09-28 | 28 | 1 | 28 | 1 | 2020-09-28 | 100%
Consultation conducted | MoJ | Completed |  | 1 | 2020-09-29 | 29 | 1 | 29 | 1 | 2020-09-29 | 100%
Consultation report from LFP (draft) | MoJ | In Progress | Completed 2nd consultation report first as was a more involved meeting and thus, more important for initial feedback and finalization | 4 | 2020-10-21 | 12 | 10
Consultation report from LFP (feedback) | POC / Technical Secretariat | Pending |  | 4 | 2020-10-22 | 21 | 1
2 Consultation
Pre-consultation discussion and strategy meeting with POC | POC / Technical Secretariat | Completed |  | 1 | 2020-10-02 | 2 | 1 | 2 | 1 | 2020-10-02 | 100%
Technical Secretariat Presentation on OGP Process and Feedback Tool | POC / Technical Secretariat | Completed |  | 2 | 2020-10-05 | 2 | 4 | 3 | 3 | 2020-10-05 | 100%
Consultation conducted | MoJ | Completed |  | 2 | 2020-10-05 | 5 | 1 | 5 | 1 | 2020-10-05 | 100%
Consultation report from LFP (draft) | MoJ | Completed |  | 4 | 2020-10-19 | 10 | 10 | 8 | 5 | 2020-10-12 | 100%
Consultation report from LFP (feedback) | POC / Technical Secretariat | In Progress |  | 4 | 2020-10-20 | 19 | 2 | 17
3 Consultation
Pre-consultation discussion and strategy meeting with POC | POC / Technical Secretariat | Completed |  | 3 | 2020-10-12 | 12 | 1 | 12 | 1 | 2020-10-12 | 100%
Technical Secretariat Presentation | POC / Technical Secretariat | Completed |  | 3 | 2020-10-13 | 13 | 1 | 13 | 1 | 2020-10-13 | 100%
Consultation conducted | MoJ | Completed |  | 3 | 2020-10-13 | 13 | 1 | 13 | 1 | 2020-10-13 | 100%
Prioritization/ranking introduced | POC / Technical Secretariat | Completed |  | 3 | 2020-10-13 | 13 | 1 | 13 | 1 | 2020-10-13 | 100%
Consultation report from LFP (draft) | MoJ | In Progress |  | 4 | 2020-10-20 | 13 | 8
Consultation report from LFP (feedback) | POC / Technical Secretariat | In Progress |  | 4 | 2020-10-21 | 20 | 1
Draft ideas distributed to stakeholders | MoJ | Pending |  | 4 | 2020-10-21 | 20 | 1
4 Consultation
Pre-consultation discussion and strategy meeting with POC | POC / Technical Secretariat | Pending |  | 4 | 2020-10-20 | 20 | 1
Technical Secretariat Presentation | POC / Technical Secretariat | Pending |  | 4 | 2020-10-21 | 21 | 1
Consultation conducted | MoJ | Pending |  | 4 | 2020-10-21 | 21 | 1
Consultation report from LFP (draft) | MoJ | Pending |  | 4 | 2020-10-22 | 21 | 2
Consultation report from LFP (feedback) | POC / Technical Secretariat | Pending |  | 4 | 2020-10-23 | 22 | 2
Draft Action Plan
Action Plan Template Completed | MoJ | Pending |  | 4 | 2020-10-21 | 20 | 1
State of Play Draft Completed | MoJ | Pending |  | 4 | 2020-10-22 | 21 | 1
Digital Governance
Stakeholder Resources and Tools
Component Brief | POC / Technical Secretariat | Completed |  | 1 | 2020-09-28 | 25 | 4 | 25 | 2 | 2020-09-26 | 100%
Feedback Template 1 Designed | POC / Technical Secretariat | Completed |  | 1 | 2020-09-28 | 23 | 5 | 23 | 5 | 2020-09-28 | 100%
Feedback Template 2 Designed | POC / Technical Secretariat | Completed |  | 1 | 2020-09-28 | 23 | 5 | 23 | 5 | 2020-09-28 | 100%
Feedback Template 1 Converted to GoogleForms | POC / Technical Secretariat | Completed |  | 1 | 2020-10-02 | 1 | 1 | 1 | 1 | 2020-10-02 | 100%
Feedback Template 2 Converted to GoogleForms | POC / Technical Secretariat | Completed |  | 2 | 2020-10-08 | 6 | 2 | 6 | 1 | 2020-10-07 | 100%
Link to Online Feedback | ADISA | Completed |  | 2 | 2020-10-08 | 8 | 1 | 7 | 1 | 2020-10-07 | 100%
1 Consultation
Pre-consultation discussion and strategy meeting with POC | POC / Technical Secretariat | Completed |  | 1 | 2020-09-29 | 29 | 1 | 29 | 1 | 2020-09-29 | 100%
Technical Secretariat Presentation on OGP Process and Feedback Tool | POC / Technical Secretariat | Completed |  | 1 | 2020-09-30 | 28 | 3 | 28 | 3 | 2020-09-30 | 100%
Consultation conducted | ADISA | Completed |  | 1 | 2020-09-30 | 30 | 1 | 30 | 1 | 2020-09-30 | 100%
Consultation report from LFP (draft) | ADISA | Completed |  | 3 | 2020-10-16 | 9 | 8 | 9 | 7 | 2020-10-15 | 100%
Consultation report from LFP (feedback) | POC / Technical Secretariat | In Progress |  | 4 | 2020-10-20 | 16 | 5
2 Consultation
Pre-consultation discussion and strategy meeting with POC | POC / Technical Secretariat | Completed |  | 2 | 2020-10-05 | 6 | 1 | 6 | 1 | 2020-10-05 | 100%
Technical Secretariat Presentation on OGP Process and Feedback Tool | POC / Technical Secretariat | Completed |  | 2 | 2020-10-09 | 9 | 1 | 9 | 1 | 2020-10-09 | 100%
Consultation Conducted | ADISA | Completed |  | 2 | 2020-10-09 | 9 | 1 | 9 | 1 | 2020-10-09 | 100%
Consultation report from LFP (draft) | ADISA | In Progress |  | 4 | 2020-10-20 | 14 | 7
Consultation report from LFP (feedback) | POC / Technical Secretariat | Pending |  | 4 | 2020-10-21 | 20 | 1
3 Consultation
Pre-consultation discussion and strategy meeting with POC | POC / Technical Secretariat | Completed |  | 4 | 2020-10-19 | 19 | 1 | 19 | 1 | 2020-10-19 | 100%
Technical Secretariat Presentation | POC / Technical Secretariat | Pending |  | 4 | 2020-10-20 | 20 | 1
Consultation conducted | ADISA | Pending |  | 4 | 2020-10-20 | 20 | 1
Consultation report from LFP (draft) | ADISA | Pending |  | 4 | 2020-10-21 | 20 | 2
Consultation report from LFP (feedback) | POC / Technical Secretariat | Pending |  | 4 | 2020-10-22 | 21 | 1
Draft ideas distributed to stakeholders | ADISA | Pending |  | 4 | 2020-10-22 | 21 | 1
Draft Action Plan
Action Plan Template Completed | ADISA | Pending |  | 4 | 2020-10-21 | 20 | 1
State of Play Draft Completed | ADISA | Pending |  | 4 | 2020-10-22 | 21 | 1
Fiscal Transparency
Stakeholder Resources and Tools
Component Brief | POC / Technical Secretariat | Completed |  | 1 | 2020-09-28 | 25 | 3 | 25 | 3 | 2020-09-28 | 100%
Feedback Template 1 Designed | POC / Technical Secretariat | Completed |  | 1 | 2020-09-28 | 23 | 5 | 23 | 5 | 2020-09-28 | 100%
Feedback Template 2 Designed | POC / Technical Secretariat | Completed |  | 1 | 2020-09-28 | 23 | 5 | 23 | 5 | 2020-09-28 | 100%
Feedback Template 1 Converted to GoogleForms | POC / Technical Secretariat | Completed |  | 1 | 2020-10-02 | 1 | 1 | 1 | 1 | 2020-10-02 | 100%
Feedback Template 2 Converted to GoogleForms | POC / Technical Secretariat | Completed |  | 2 | 2020-10-08 | 6 | 2 | 6 | 1 | 2020-10-07 | 100%
Link to Online Feedback | MoFE | Completed |  | 2 | 2020-10-08 | 8 | 1 | 7 | 1 | 2020-10-07 | 100%
1 Consultation
Consultation Conducted | MoFE | Completed |  | - | 2020-09-15 | 15 | 1 | 15 | 1 | 2020-09-15 | 100%
Consultation report from LFP (draft) | MoFE | In Progress |  | 4 | 2020-10-21 | 12 | 10
Consultation report from LFP (feedback) | POC / Technical Secretariat | Pending |  | 4 | 2020-10-22 | 21 | 1
2 Consultation
Pre-consultation discussion and strategy meeting with POC | POC / Technical Secretariat | Completed |  | 1 | 2020-09-29 | 29 | 1 | 29 | 1 | 2020-09-29 | 100%
Technical Secretariat Presentation on OGP Process and Feedback Tool | POC / Technical Secretariat | Completed |  | 1 | 2020-09-30 | 28 | 3 | 28 | 3 | 2020-09-30 | 100%
Consultation conducted | MoFE | Completed |  | 1 | 2020-09-30 | 30 | 1 | 30 | 1 | 2020-09-30 | 100%
Consultation report from LFP (draft) | MoFE | In Progress |  | 4 | 2020-10-21 | 12 | 10
Consultation report from LFP (feedback) | POC / Technical Secretariat | Pending |  | 4 | 2020-10-22 | 21 | 1
3 Consultation
Pre-consultation discussion and strategy meeting with POC | POC / Technical Secretariat | Completed |  | 2 | 2020-10-05 | 5 | 1 | 5 | 1 | 2020-10-05 | 100%
Technical Secretariat Presentation | POC / Technical Secretariat | Completed |  | 3 | 2020-10-15 | 15 | 1 | 15 | 1 | 2020-10-15 | 100%
Consultation conducted | MoFE | Completed |  | 3 | 2020-10-15 | 15 | 1 | 15 | 1 | 2020-10-15 | 100%
Prioritization/ranking introduced | MoFE | Completed |  | 3 | 2020-10-15 | 15 | 1 | 15 | 1 | 2020-10-15 | 100%
Consultation report from LFP (draft) | MoFE | In Progress |  | 4 | 2020-10-21 | 12 | 10
Consultation report from LFP (feedback) | POC / Technical Secretariat | Pending |  | 4 | 2020-10-22 | 21 | 1
Draft ideas distributed to stakeholders | MoFE | Pending |  | 4 | 2020-10-22 | 21 | 1
Draft Action Plan
Action Plan Template Completed | MoFE | Pending |  | 4 | 2020-10-21 | 20 | 1
State of Play Draft Completed | MoFE | Pending |  | 4 | 2020-10-22 | 21 | 1
Anti-Corruption
Stakeholder Resources and Tools
Component Brief | POC / Technical Secretariat | Completed |  | 1 | 2020-09-28 | 25 | 3 | 25 | 3 | 2020-09-28 | 100%
Feedback Template 1 Designed | POC / Technical Secretariat | Completed |  | 1 | 2020-09-25 | 23 | 1 | 23 | 2 | 2020-09-26 | 100%
Feedback Template 2 Designed | POC / Technical Secretariat | Completed |  | 1 | 2020-09-28 | 23 | 5 | 23 | 5 | 2020-09-28 | 100%
Feedback Template 1 Converted to GoogleForms | POC / Technical Secretariat | Completed |  | 1 | 2020-10-02 | 1 | 1 | 1 | 1 | 2020-10-02 | 100%
Feedback Template 2 Converted to GoogleForms | POC / Technical Secretariat | Completed |  | 2 | 2020-10-08 | 6 | 2 | 6 | 1 | 2020-10-07 | 100%
Link to Online Feedback | MoJ | Completed |  | 2 | 2020-10-08 | 8 | 1 | 7 | 1 | 2020-10-07 | 100%
1 Consultation
Technical Secretariat Presentation on OGP Process and Feedback Tool | POC / Technical Secretariat | Completed |  | 1 | 2020-09-25 | 25 | 1 | 25 | 1 | 2020-09-25 | 100%
Consultation conducted | MoJ | Completed |  | 1 | 2020-09-25 | 25 | 1 | 25 | 1 | 2020-09-25 | 100%
Consultation report from LFP (draft) | MoJ | Pending |  | 4 | 2020-10-20 | 14 | 7 | 8 | 7 | 2020-10-14 | 100%
Consultation report from LFP (feedback) | POC / Technical Secretariat | Pending |  | 4 | 2020-10-21 | 20 | 1
2 Consultation
Pre-consultation discussion and strategy meeting with POC | POC / Technical Secretariat | Completed |  | 1 | 2020-09-28 | 28 | 1 | 28 | 1 | 2020-09-28 | 100%
Consultation conducted | MoJ | Completed |  | 1 | 2020-09-29 | 29 | 1 | 29 | 1 | 2020-09-29 | 100%
Consultation report from LFP (draft) | MoJ | Pending |  | 4 | 2020-10-20 | 14 | 7
Consultation report from LFP (feedback) | POC / Technical Secretariat | Pending |  | 4 | 2020-10-21 | 20 | 1
3 Consultation
Pre-consultation discussion and strategy meeting with POC | POC / Technical Secretariat | Completed |  | 3 | 2020-10-13 | 13 | 1 | 13 | 1 | 2020-10-13 | 100%
Technical Secretariat Presentation | POC / Technical Secretariat | Completed |  | 3 | 2020-10-14 | 14 | 1 | 14 | 1 | 2020-10-14 | 100%
Consultation conducted | MoJ | Completed |  | 3 | 2020-10-14 | 14 | 1 | 14 | 1 | 2020-10-14 | 100%
Prioritization/ranking introduced | MoJ | Completed |  | 3 | 2020-10-14 | 14 | 1 | 14 | 1 | 2020-10-14 | 100%
Consultation report from LFP (draft) | MoJ | Pending |  | 4 | 2020-10-20 | 14 | 7
Consultation report from LFP (feedback) | POC / Technical Secretariat | Pending |  | 4 | 2020-10-21 | 20 | 1
Draft ideas distributed to stakeholders | MoJ | Pending |  | 4 | 2020-10-22 | 21 | 1
Draft Action Plan
Action Plan Template Completed | MoJ | Pending |  | 4 | 2020-10-21 | 20 | 1
State of Play Draft Completed | MoJ | Pending |  | 4 | 2020-10-22 | 21 | 1
National Agency for Information Society (NAIS)
Email about stakeholder feedback uploads | POC / Technical Secretariat | Completed |  | 1 | 2020-10-02 | 1 | 2 | 1 | 2 | 2020-10-02 | 100%
Email about online feedback input | POC / Technical Secretariat | Completed |  | 1 | 2020-10-02 | 2 | 1 | 2 | 1 | 2020-10-02 | 100%
Review OGP website for all updates 1 | POC / Technical Secretariat | Completed |  | 2 | 2020-10-07 | 6 | 2 | 6 | 4 | 2020-10-09 | 100%
Review OGP website for all updates 2 | POC / Technical Secretariat | Pending |  | 4 | 2020-10-20 | 20 | 1
Approval of the Final Action Plan
Amendments and improvements to draft action plan | POC / Technical Secretariat & LFPs |  |  | 6 | November
Approval of the Final Action Plan | Cabinet Approval |  |  | 11 | 2020-12-10
Action Plan is sent to the OGP structures